|  |  |  |
| --- | --- | --- |
| **PROJECT 6** Name: **LICENSING** | | |
| **Objective:** Enable communities to have increase awareness on new proposed liquor outlets and promote community action | | |
| **Project Tasks**. | | Aligned National RBA Activity (where applicable) |
| **Key Tasks/Actions** | Completion |
| 1. Put together Resource materials 2. Engage Stakeholders in particular Community Public Health (DHB)   Note: We have just formed a collaborative Partnership with CPH (CAAT) Community Action Alcohol Team. This is an initiative which has a proactive approach to liquor licensing in the community. The CAAT team involves Community Law, CPH –Licensing and alcohol health promoters and CAYAD providing opportunities for communities to better prepare to respond to liquor applications.   1. Reach 3 communities (particularly those identified as low socio-economic -decile groups) 2. Submissions on Liquor licensing applications from communities increased | August 2017  August 2017  Sept/Oct 2017  June 2018  June 2018 | 2  Engage with and support organisations/community groups to plan and deliver community action initiatives to reduce alcohol and other drug related harm affecting young people[[1]](#footnote-1)*.*  3  Design, deliver and support awareness-raising activities[[2]](#footnote-2) that provide opportunity for informed discussion and debate, increase knowledge[[3]](#footnote-3) and/or create behaviour change around the use of alcohol and other drugs. |
| Internal RBA  MOH Reporting requirements | Quarterly 1, 2, 3, 4  May 20th Action Plan  6 m progress report  May 20th Action Plan  ANNUAL June 20th |  |

1. *These are initiatives led by the community with CAYAD support or CAYAD led with strong community involvement* [↑](#footnote-ref-1)
2. *This can include supporting national campaigns* [↑](#footnote-ref-2)
3. *This can include knowledge of evidence-based actions to reduce harm from AOD*  [↑](#footnote-ref-3)